## Time Log
Time Recording Log
Name: | Vanessa Sanders
Date: | 2020-10-21
Date | Start | Stop | Beak time | Actual Time | Phase | Comment
2020-10-21 | 11 | 12.32 | 0 | 1.32 |  | I shared some documents with everyone and had a first team meeting and then starting working on use case scenarios. Finished approx two of those. Then I went in an checked through the use case diagram start up.
2020-10-24 | 1 | 1.47 | 0 | 1.47 |  | I created and revised some use case scenarios and worked on the data dictionary
2020-10-25 | 9.15 | 11.52 | 0.3 | 2.07 |  | I revised the data dictionary and finsihed off the rest of the use case diagram
2020-10-31 | 9 | 9.2 | 0 | 0.2 |  | I made up a google document and shared with will everyone and we have a meeting
2020-11-01 | 3 | 3.3 | 0 | 0.3 |  | I made up my own estimates
2020-11-01 | 11 | 12 | 0 | 1 |  | I worked on reviewing others estimates and coming up with a meeting time
2020-11-02 | 9 | 10.3 | 0 | 1.3 |  | I formatted and calculated with the group
2020-11-09 | 9.15 | 10.15 | 0 | 1 |  | I started working on the class diagram
2020-11-10 | 10 | 11 | 0 | 1 |  | I worked on the class diagram
2020-11-11 | 3.3 | 4 | 0 | 0.3 |  | I worked on the class diagram
2020-11-11 | 9.4 | 10.05 | 0 | 0.25 |  | I worked on the functions of the classes in the class diagram
2020-11-14 | 3.3 | 4.3 | 0 | 1 |  | I worked on the sequence diagrams
Total |  |  |  | 11.21